## Slide 1
Situation / Problem statement / Key-facts
Newborns in incubators are highly vulnerable to sudden changes in vital signs, yet current monitoring largely depends on periodic manual checks and threshold-based alarms.
Manual, periodic checks can delay detection of abnormal vitals
Static threshold alarms react only after a parameter crosses a fixed limit, by which point deterioration may already be underway
This increases the cognitive and physical load on NICU staff managing multiple infants
  There is a clear need for an intelligent, continuous, predictive monitoring solution
Objectives & Expected Result
Build a predictive monitoring system (NAVAAYU) that continuously analyzes a neonate's vital signs to anticipate health deterioration before it becomes critical
Surface real-time, data-backed insights for doctors and medical staff
Enable earlier detection of abnormalities and reduce missed critical events
Improve staff response time and reduce NICU monitoring burden
Ultimately improve neonatal safety and overall care quality
Deliverables or milestone activities
Pre-condition & Support needed
Key Support
Clinical mentorship from hospital medical staff, hospital IT/infra support for edge integration, and access to incubator hardware for testing
Pre-condition
Edge AI deployment capability on incubator hardware for real-time, on-device inference
Federated learning setup to train the model across hospital sites without centralizing patient data
Hospital partnership for real-world data access, model validation, and regulatory/ethical clearance
Project team
Steering | Project team
TBD | Asawari Pawar – ML Engineer Tanvee Darwatkar – Developer Deepti Patra – Project Manager
Sponsor | TBD | Project lead | Krishna Vaghela
Deliverables/ Milestones | Date
Project charter finalization | 22 July 2026
Prototype development (hardware + sensors) | 23 July 2026
ML model development for vitals prediction | 26 July 2026
Pilot testing (single incubator/unit) | 26–29 July 2026
Alert system integration & validation | 26–29 July 2026
Deployment of prototype | 29 July 2026
Deployment across NICU | Future
Meeting Frequency: Core Team- every 2–3 weeks
Project Charter - NAVAAYU

## Slide 2
Milestones – Critical path (Gantt Chart)
NAVAAYU
Decisions | Made/Required | Impact
Lead: Krishna Vaghela
Date: 22 July 2026
Key Issues | Status
Hospital data access | Informed
Hardware reliability | Informed
Model accuracy | Informed
Achievements
Consulted doctors/hospital staff for technical & medical insight
Basic frontend developed
ML model development in progress
Next Steps | Owner
Complete ML model for vitals prediction | Asawari Pawar
Integrate alert system | Tanvee Darwatkar
Pilot testing on incubator | Deepti Patra
Status | Schedule | Resources | Scope | Timing | Deployment | Effectiveness
Defined | Allocated | Defined | Defined | Planned | KPIs to be finalised
On-track
Risks but actions taken
Off-track
Not started
Key Prototype Hardware | Cost
Rasberry PI 5 | 9000
Micro SD Card | 1000
Rasberry Pi adapter | 1000
Milestone | 22 Jul | 23 Jul | 24 Jul | 25 Jul | 26 Jul | 27 Jul | 28 Jul | 29 Jul | Status
Project charter finalization |  |  |  |  |  |  |  |  | 
Prototype development |  |  |  |  |  |  |  |  | 
ML model development |  |  |  |  |  |  |  |  | 
Pilot testing & alert integration |  |  |  |  |  |  |  |  | 
Deployment of prototype |  |  |  |  |  |  |  |  | 
Help needed
Cost | Baseline: <if available> | YTD:
Benefits | Baseline: | YTD:
Project Progress Report - NAVAAYU

## Slide 3
Value Proposition (Motive for doing project)
This project will implement a predictive, AI-driven monitoring system for neonatal incubators, enabling early detection of health deterioration before it becomes critical. The expected outcome is faster clinical response and better-informed medical decisions, resulting in improved neonatal safety and reduced risk during the most vulnerable stage of life.
NAVAAYU: Predicts abnormal vitals in real time using Edge AI + federated learning across incubators, enabling doctors to intervene earlier, improving neonatal safety and outcomes.
A strong value proposition should ideally answer –
What problem are we solving?
What benefit will be delivered?
How will success be measured?
Why does it matter to the business?
A strong Value Proposition in a Project Charter clearly articulates the business benefit, measurable impact, and strategic value the project delivers.
Cost Reduction
Productivity Improvement
Customer Experience Enhancement
Revenue Growth
Risk Mitigation
Quality Improvement
Employee Experience
Business Agility
Data & Analytics
Strategic Transformation